|  |  |
| --- | --- |
| Assessment 3: Group Project | |
| Project Name: | 5G |
| Due Date: | June 10th |

This is the tracking document for our group writing project. We’ll use this document to share details, resources, and schedules for our project. Please keep this document up-to-date as we work.

|  |  |  |
| --- | --- | --- |
| Participants | | |
| Name | Role | Contact information |
| Fang Sen | Leader | 1285233846@qq.com |
| Xia Enze | Member | 1356654919@qq.com |
| Zhu He | Member | 1428879112@qq.com |
| Zhao Jiawei | Member | z18235136582@icloud.com |

|  |  |  |
| --- | --- | --- |
| Milestones | | |
| Milestone name | Target date | Status |
| Building Slack Channel | 7 APRIL | END |
| Wiki design | 24 MAY | END |
| User guide | 6 June | END |
| Information Security Plan | 8 June | END |
| Report Writing (first-draft) | 9 June | END |
| Oral Presentation | 12 June | PROCEEDING |
|  |  |  |
|  |  |  |
|  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| Tracking calendar | | | |
|  | April | Enter month name | Enter month name |
| 1 | Group meeting | 22 April | 22 April |
| 2 | Selecting templates for wiki web design | 25 May | 25 May |
| 3 | Familiar with the functions of Fandom | 25 May | 25 May |
| 4 | Query information about open technology | 2 June | 2 June |
| 5 | Collect relevant documents and sort them | 3 June | 3 June |
| 6 | Determine the first version of the wiki page | 4 June | 4 June |
| 7 | Publish Wiki page | 5 June | 5 June |
| 8 | Publish blog | 5 June | 5 June |
| 9 | Write user manual | 6 June | 6 June |
| 10 | Discuss the relevant content of the information security plan | 8 June | 8 June |
| 11 | Build the overall framework of our report | 9 June | 9 June |
| 12 | Query related references | 9 June | 9June |
| 13 | Draft report | 9 June | 9 June |
| 14 | Edit report | 9 June | 9 June |
| 15 | PPT required to make the report | 10 June | 10 June |
| 16 |  |  |  |
| 17 |  |  |  |
| 18 |  |  |  |
| 19 |  |  |  |
| 20 |  |  |  |
| 21 |  |  |  |
| 22 |  |  |  |
| 23 |  |  |  |
| 24 |  |  |  |
| 25 |  |  |  |
| 26 |  |  |  |
| 27 |  |  |  |
| 28 |  |  |  |